VE meeting

May 7, 2004

Attendees: Trish Ververs, Randy Pausch, Jesse Schell, Allison Styer, Jason Pratt, Jeremy Higgins

The meeting was spent primarily getting an update from CMU on their efforts on running the experiment to achieve the 100% performance improvement.

Data collection update:

- Testing has been done with only Allison and Rob. They’ve run themselves over and over again to get the appropriate workload level. The next step is to collect naïve subject data. The goal is to run 6-8 naïve subjects.

- Rob and Allison will run some subjects this weekend

- Biggest concern: They will do what they can. But they are obviously unable to promise the end results. If it doesn’t work there is nothing more they can do. No more iterations will be tried. The biggest constraint is that the final presentations for ETC students is Tuesday, so workload is high this week. The transition is in place and Jason is available but he is also supporting 2 ETC projects, so he is on the same schedule. There is no concern that information will be lost. Rob will be available this summer if there are any questions.

- The goal is to run 2 or 3 blocks of trials (each block has 3 status reports) per condition (mitigated/unmitigated)

- The condition will be blocked (run all mitigated trials together and all unmitigated trials together)

- Counterbalance the order of mitigation (1/2 the subjects see mitigated condition first,1/2 subjects see unmitigated condition first)

- Consider drafting a one-page questionnaire. Ask about gaming experience, age, strategy used to remember numbers.

Important dates:

- May 14 deadline: Collect performance data (no gauge information needs to be recorded)

- May 25 deadline: confirm parameters for Pre-CVE (setup experiment with gauges). Have experimental protocol done and mitigation strategy coded. Lead by Stephen

- Develop a transition plan. Randy is back next week.

Additional information:

- CMU has the most recent IHMC architecture installed (CMU is running version 1.6.3). This was confirmed by Jason and Jeremy

- Panda is integrated as dpi (data provider interface)

- Engagement Index set to 20-second window; As per Jeremy’s instructions CMU will confirm that EI is set to 10240 (engagement property file)

- Panda is logging all appropriate events

Action Items:

Action: Jesse Schell: Jesse will send out an email laying out the activities CMU plans to perform and what they can and cannot do between now and May 14

Action: Jason Pratt: Confirm Engagement Index is set to 10240 in engagement property file

Trish is available via cell phone this weekend for any last minute issues that might arise (973-652-5989)